## HW-Milestone tracker
Ultrasmall proper working 11kW+3kW
| HW Design |  |  |  |  | Procurement | Prototype PCB |  |  | Mechanical |  |  | Testing | [6 empty] | Release |  |  | Project
Task | Requirements Freeze | Component Selection | Schematic Design | PCB Layout | Design Review | Component Ordering | Proto Gerber Release | PCB Prototype Manufacturing | PCB Prototype Assembly | Mechanical Design | Proto Mechanical Design Release | Mechanical Prototype Manufacturing | Test Plan Preparation | Test Plan Approval | PCB Bring-up | Electrical Testing | SW Integration | Final Integration | Test Report | Final Schematics | Final Layout | Final BOM | Project Closure / Milestone Complete
Owner
Planned Start
Planned Finish
Actual Start
Actual Finish
Status
Dependency
Remarks
Separate Small DCDC 2kW with planar
| HW Design |  |  |  |  | Procurement | Prototype PCB |  |  | Mechanical |  |  | Testing | [6 empty] | Release |  |  | Project
Task | Requirements Freeze | Component Selection | Schematic Design | PCB Layout | Design Review | Component Ordering | Proto Gerber Release | PCB Prototype Manufacturing | PCB Prototype Assembly | Mechanical Design | Proto Mechanical Design Release | Mechanical Prototype Manufacturing | Test Plan Preparation | Test Plan Approval | PCB Bring-up | Electrical Testing | SW Integration | Final Integration | Test Report | Final Schematics | Final Layout | Final BOM | Project Closure / Milestone Complete
Owner
Planned Start
Planned Finish | 2026-10-16
Actual Start
Actual Finish
Status
Dependency
Remarks
Separate Small OBC 6.6kW with planar
| HW Design |  |  |  |  | Procurement | Prototype PCB |  |  | Mechanical |  |  | Testing | [6 empty] | Release |  |  | Project
Task | Requirements Freeze | Component Selection | Schematic Design | PCB Layout | Design Review | Component Ordering | Proto Gerber Release | PCB Prototype Manufacturing | PCB Prototype Assembly | Mechanical Design | Proto Mechanical Design Release | Mechanical Prototype Manufacturing | Test Plan Preparation | Test Plan Approval | PCB Bring-up | Electrical Testing | SW Integration | Final Integration | Test Report | Final Schematics | Final Layout | Final BOM | Project Closure / Milestone Complete
Owner
Planned Start
Planned Finish | 2026-10-16
Actual Start
Actual Finish
Status
Dependency
Remarks

## SW-Milestone tracker
Offline Car Voice Assistant (AutoAI) - SW Milestone Tracker ¦ 19 Oct - 30 Dec 2026 ¦ 51 working days
| Research & Requirements |  | Development cycle |  |  |  | Testing |  |  | Bug fixing |  |  | Deployment
Task | Research & Feasibility | Requirements Freeze | M1 Car Data Layer | M2 Q&A Engine | M3 Voice Pipeline | M4 App UI & Features | Test Plan | Module 1-2 Testing | Module 3-4 & System Testing | Bug Fix M1-M2 | Bug Fix M3-M4 | Regression Testing | Packaging & Install | UAT & Release
Owner
Planned Start | 2026-10-19 | 2026-10-23 | 2026-10-26 | 2026-11-02 | 2026-11-16 | 2026-11-23 | 2026-11-27 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-17 | 2026-12-23 | 2026-12-25 | 2026-12-28
Planned Finish | 2026-10-22 | 2026-10-24 | 2026-10-30 | 2026-11-06 | 2026-11-20 | 2026-11-26 | 2026-11-28 | 2026-12-04 | 2026-12-12 | 2026-12-16 | 2026-12-22 | 2026-12-24 | 2026-12-26 | 2026-12-30
Actual Start
Actual Finish
Status | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
Dependency | - | Research | Req. Freeze | M1 | M2 | M2, M3 | Req. Freeze | M1, M2, Test Plan | M3, M4 | Testing | Testing | Bug fixes | Regression | Packaging
Remarks | 3 working day(s). RAG vs SQL decision, 4 GB RAM baseline, model shortlist, car-manual data audit | 2 working day(s). Scope, supported cars, languages, acceptance criteria signed off | 5 working day(s). Structured car-facts SQL tables (specs, service, warning lights) + manual import/OCR | 5 working day(s). Question router: SQL facts first, FTS/vector retrieval for manual text, Qwen answer + citations | 5 working day(s). VAD/Whisper/Piper hardening, barge-in, Hindi check, latency tuning | 4 working day(s). Knowledge, Maintenance, Music, Settings screens; export/backup | 2 working day(s). Test cases, real-manual Q&A gold set, device test matrix | 5 working day(s). Answer accuracy, citation and refusal tests on real manuals | 6 working day(s). End-to-end voice tests, car-noise/mic tests, 4 GB device benchmark | 3 working day(s). Data/retrieval/answer defects | 4 working day(s). Voice/UI defects, performance tuning | 2 working day(s). Full regression run on all modules | 2 working day(s). Offline installer, model/asset setup check on a clean machine | 3 working day(s). User acceptance check, release build, user guide, handover (Day 51)

## Week-wise Plan
Week-wise Plan - Offline Car Voice Assistant
Off: Sundays ¦ 1st, 3rd & 5th Saturdays ¦ 20 Oct ¦ 7-15 Nov holiday shutdown. 2nd & 4th Saturdays are working days.
Week | Dates | Working Days | Day # | Phase / Module | Key Activities | Deliverable | Status
W1 | 19 Oct - 24 Oct | 5 | 1-5 | Research & Requirements | Study existing RAG + voice stack; decide RAG vs SQL; benchmark RAM/latency on 4 GB target; collect real car manuals; freeze requirements | Feasibility note + frozen requirements | Not Started
W2 | 26 Oct - 31 Oct | 5 | 6-10 | M1 Car Data Layer | Design car-facts SQL schema; extract specs/service/warning-light data from manuals; manual import + OCR for scanned PDFs | Car data DB with 2-3 real cars loaded | Not Started
W3 | 02 Nov - 06 Nov | 5 | 11-15 | M2 Q&A Engine | Question router (SQL lookup vs manual retrieval); tune FTS/vector search; Qwen prompts, citations, refusal | Text Q&A working end-to-end | Not Started
- | 07 Nov - 15 Nov | 0 | - | HOLIDAY SHUTDOWN | - | -
W4 | 16 Nov - 21 Nov | 5 | 16-20 | M3 Voice Pipeline | Harden VAD/Whisper/Piper; barge-in and echo; Hindi recognition check; reduce response latency | Stable voice-to-voice flow | Not Started
W5 | 23 Nov - 28 Nov | 6 | 21-26 | M4 App UI + Test Plan | Finish app screens & export; write test plan, Q&A gold set and device test matrix | UI complete + approved test plan | Not Started
W6 | 30 Nov - 05 Dec | 5 | 27-31 | M1-M2 Testing | Test data layer and Q&A: answer accuracy, citations, refusals on real manuals | M1-M2 test report | Not Started
W7 | 07 Dec - 12 Dec | 6 | 32-37 | M3-M4 & System Testing | End-to-end voice tests, car-noise/real-mic tests, 4 GB device benchmark, bug logging | System test report + bug list | Not Started
W8 | 14 Dec - 19 Dec | 5 | 38-42 | Bug Fixing | Fix data/Q&A defects, then start voice/UI defects | M1-M2 bugs closed | Not Started
W9 | 21 Dec - 26 Dec | 6 | 43-48 | Bug Fixing + Regression + Packaging | Finish voice/UI fixes and performance tuning; full regression; offline installer, clean-machine check | All critical bugs closed, installer ready | Not Started
W10 | 28 Dec - 30 Dec | 3 | 49-51 | UAT & Release | User acceptance check, release build, user guide, handover | Release v1.0 (Day 51) | Not Started
Total | 19 Oct - 30 Dec | 51 |  | 31 Dec kept as buffer. 25 Dec counted as working; adjust if it is a holiday.